## Sheet1
Tasks | Start Date | Duration
Literature review | 2021-10-10 | 30
Explore Hardware | 2021-11-10 | 30
Tools Learning | 2021-12-10 | 60
Image Sensor Integration | 2022-02-10 | 30
IP cores designing | 2022-03-10 | 60
Testing | 2022-05-10 | 30
Documentation | 2022-06-10 | 30
44752